## Data
Project Name: |  | Dungeon Crawl |  |  | Requirements Traceability
Project Description: |  | Roguelikes are one of the oldest types of video games, the earliest ones were made in the 70s, they were inspired a lot by tabletop RPGs. The task will be to create a roguelike!
Requirements |  |  |  |  | Testing | [8 empty] | Comment | Defects
Req. ID | Requirements Description | Requirement Type |  | Test Condition | Test Description | Test Case | Tester | Sanyi | Dina | Gergő | Balázs | Bence | András | Comment | Defect ID | Defect Description
1 | Movement Create a game logic which restricts the movement of the player so s/he cannot run into walls and monsters. | Functional | Moving up |  | Verify that you can move the character up with the W key or up arrow. | VG-T108 | Bence |  | Pass |  |  | Pass
|  | Functional | Moving down |  | Verify that you can move the character down with the S key or down arrow. | VG-T111 | Bence |  | Pass |  |  | Pass
|  | Functional | Moving left |  | Verify that you can move the character left with the A key or left arrow. | VG-T112 | Bence |  | Pass |  |  | Pass
|  | Functional | Moving right |  | Verify that you can move the character Right with the D or right arrow. | VG-T113 | Bence |  | Pass |  |  | Pass
|  | Functional | Moving through walls |  | Verify that character can't go through walls. | VG-T117 | Bence |  | Pass |  |  | Pass
|  | Functional | Moving through water |  | Verify that character can't go through water. | VG-T118 | Bence |  | Blocked |  |  | Blocked
|  | Functional | Moving through trees |  | Verify that character can't go through trees. | VG-T119 | Bence |  | Blocked |  |  | Blocked
|  | Functional | The opponent's movement |  | Verify that after the character moves one block the enemy moves one aswell | VG-T147 | Bence |  | Pass |  |  | Pass
|  | Functional | Diagonal movement |  | Verify that the the characters can not move diagonally. | VG-T153 | Bence |  | Fail |  |  | Fail |  | #7 |  | If you press the right and up arrows at the same time, the character starts diagonally.
|  | Functional | Ghost - Changing locations |  | Verify that after 5 turn/move the gohsts are changing location | VG-T155 | Bence |  | Blocked |  |  | Blocked
|  | Functional | Follow - Skeletons |  | Verify that if you go close to a skeleton it will follow you. | VG-T159 | Bence |  | Pass |  |  | Pass
|  | Functional | Follow - Ghosts |  | Verify that if you go close to a ghost it will follow you. | VG-T160 | Bence |  | Blocked |  |  | Blocked
|  | Functional | Follow - Multiple enemy |  | Verify that if you go close to an enemy while you already being followed another will follow you. | VG-T161 | Bence |  | Pass |  |  | Pass
|  | Functional | Stairs - Go down |  | Verify that you can go down the stairs. | VG-T189 | Bence |  | Pass |  |  | Pass
|  | Functional | Stairs - Go up |  | Verify that you can go down the stairs. | VG-T190 | Bence |  | Pass |  |  | Pass
|  | Functional | Hidden room behind door. |  | Verify that you don’t see what’s behind the door until you go through it. | VG-T191 | Bence |  | Pass |  |  | Pass
|  | Functional | Revaled room stays revaled. |  | Verify that you don’t see what’s behind the door until you go through it. | VG-T192 | Bence |  | Pass |  |  | Pass
2 | Doors Create doors in the dungeon that open by using keys. | Functional | Visibility of doors |  | Test that there are these doors on the map | VG-T107 | Dina |  | Pass |  |  | Pass
|  | Functional | Type of doors |  | Test that there are different types of doors on this map | VG-T124 | Dina |  | Blocked |  |  | Blocked
|  | Functional | Open doors |  | Test that you can go through those open doors | VG-T125 | Dina |  | Blocked |  |  | Blocked
|  | Functional | Closed doors |  | Test your ability to pass through closed doors | VG-T126 | Dina |  | Blocked |  |  | Blocked
|  | Functional | Closed door with a key |  | Test that you can pass through a closed door if you have a key | VG-T127 | Dina |  | Blocked |  |  | Blocked
3 | Inventory Create a feature that allows the hero to pick up an item. Show picked up items in the inventory list. | Functional | Picked up sword/item disappear |  | Try to pick up a sword, and check if it disappears on the map | VG-T110 | Gergő | Pass |  | Pass
|  | Functional | Pick up a 2 items |  | Try to pick up a sword and after try to pick up a key | VG-T115 | Gergő | Pass |  | Pass
|  | Functional | Move over the items |  | Test moving over the items | VG-T120 | Gergő | Pass |  | Pass
|  | Functional | Pick up an item with pressing valid button |  | Try to pick up an item with pressing valid button | VG-T121 | Gergő | Pass |  | Pass
|  | Functional | Pick up an item with pressing invalid button |  | Try to pick up an item with pressing invalid button | VG-T122 | Gergő | Pass |  | Pass
|  | Functional | Pick up a sword - Change of the character's look |  | Check whether the character's look changes after the user picked up a sword | VG-T154 | Gergő | Pass |  | Pass
|  | Functional | Starting inventory |  | The inventory should be empty at the start of the game. | VG-T129 | Sanyi | Fail |  | Fail |  |  |  |  | #19 | If the player starts a new game from the menu, the character retains it's inventory, health, and the level where he was. With this the player can have more items, than what can be shown in a single line.
|  | Functional | Using a a non-reusable item |  | Using an item, that's "consumed" after it is used should decrease it's quantity in the inventory. | VG-T131 | Sanyi | Blocked |  | Blocked
4 | Keys Create doors in the dungeon that open by using keys. o There are two new square types, closed door, and open door. o The hero cannot pass through a closed door, unless it has a key in his/her inventory. Then it becomes an open door. | Functional | Visibility of keys - Start of the game |  | Check whether the keys are shown on the map correctly | VG-T128 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Visibility of keys - Character is on it |  | Check whether the z-index of the character is higher than the z-index of the "key" item | VG-T132 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Visibility of keys - Pick up the key |  | Check whether it is possible for the user to pick up a key | VG-T133 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Visibility of keys - Leaving the tile without picking up the key |  | Check whether the key remains visible if the character leaves the tile without picking it up | VG-T134 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Using a key - There is a key in the inventory |  | Check whether the user can open a door using a key | VG-T135 | Balázs |  |  |  | Blocked |  | Blocked
|  | Functional | Using a key - There is no key in the inventory |  | Check whether the user can open a door without having a key in the inventory | VG-T136 | Balázs |  |  |  | Blocked |  | Blocked
5 | Map Create maps that have more varied scenery. | Functional | Map - Map is visible |  | Check if game loads a map | VG-T137 | András |  |  |  | Pass |  | Pass
|  | Functional | Map - Tile file existing (graphics) |  | Check if a tile file is existing | VG-T143 | András |  |  |  | Pass |  | Pass
|  | Functional | Map - Load map with tiles (graphics) |  | Check if game loads a map correctly with a tile file (graphics) | VG-T145 | András |  |  |  | Pass |  | Pass
|  | Functional | Map - Random map generating |  | Check if game loads a random map | VG-T185 | András |  |  |  | Pass |  | Pass
|  | Functional | Map - Random new map with empty inventory |  | Check if game loads a random new map and inventory is empty | VG-T195 | András |  |  |  | Fail |  | Fail |  | #19 | If the player starts a new game from the menu, the character retains it's inventory, health, and the level where he was. With this the player can have more items, than what can be shown in a single line.
|  | Functional | Map - New part of map is visible when using doors |  | Check if a new part of map loads when using doors | VG-T197 | András |  |  |  | Pass |  | Pass
6 | Attack Make the hero to able to attack monsters by moving into them. | Functional | Attacking enemies |  | Check what happens, when you attack an emey. | VG-T150 | Sanyi | Fail |  | Fail
|  | Functional | Attacking a wall |  | Check what happens, when you attack a part of the wall. | VG-T151 | Sanyi | Pass |  | Pass
|  | Functional | Health - HP limit |  | Check what happens if you lost all your HP | VG-T193 | Sanyi | Fail |  | Fail
|  | Functional | Health - HP after new game |  | Check what happens if you lost some of your hp and start a new game | VG-T194 | Sanyi | Fail |  | Fail
7 | Resolution Extra function | Functional | Resolution - After opening the main menu from game |  | Check the resolution does not change when opening the main menu from game | VG-T187 | András |  |  |  | Fail |  | Fail
|  | Functional | Resolution - After quitting from the option menu |  | Check whether the value of the resolution button remains after quitting from the options menu and then coming back to it | VG-T184 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - size of the window after clicking on the new game button |  | Check if the application window can be resized after starting a new game | VG-T181 | Balázs |  |  |  | Fail |  | Fail |  | #23-26 | The window size of the menu after starting the program is 800x600. After clicking on the new game button the size of the window changes
|  | Functional | Full screen checkbox - activating after error message |  | Check whether the error message disappears after going full screen | VG-T177 | Balázs |  |  |  | Fail |  | Fail |  | #18 | In options, when you selected 1920x1080 option you get an error message, and after that you move your mouse over the full screen checkbox, the checkbox is not highlighted, and if you tick the checkbox, nothing happens
|  | Functional | Full screen checkbox - exit from full screen mode with ESC |  | Check whether the user can activate the checkbox with a mouse | VG-T176 | Balázs |  |  |  | Fail |  | Pass |  | #21 | Full-screen mode not working properly
|  | Functional | Full screen checkbox - activate with mouse |  | Check whether the user can activate the checkbox with a mouse | VG-T175 | Balázs |  |  |  | Fail |  | Pass |  | #21 | Full-screen mode not working properly
|  | Functional | Full screen checkbox - activate with only using keyboard |  | Check whether the user can activate the checkbox with only keyboard | VG-T174 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - select value from dropdown list with the mouse (with a monitor without 1920x1080 support) |  | Check whether the user can select an option from the dropdown list that is not supported by the monitor | VG-T173 | Balázs |  |  |  | Blocked |  | Blocked
|  | Functional | Resolution - select value from dropdown list with the mouse (with a monitor that supports all the possible resolutions) |  | Check whether the user can select the desired option from the dropdown list with mouse | VG-T172 | Balázs |  |  |  | Fail |  | Fail |  | #21,26 | All sizes are supported, but application does not change to all of resolutions (only 800x600 and 1280x720 works)
|  | Functional | Resolution - select value from dropdown list with enter |  | Check whether the user can select the desired option from the dropdown list with enter | VG-T171 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - select value from dropdown list with space |  | Check whether the user can select the desired option from the dropdown list with space | VG-T170 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - navigation inside the dropdown list using keyboard only |  | Check whether the user can highlight the desired option from the dropdown list using only keyboard | VG-T169 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - open dropdown list with mouse |  | Check whether the user can open the dropdown list with mouse | VG-T168 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - open dropdown list with enter |  | Check whether the user can open the dropdown list with enter | VG-T167 | Balázs |  |  |  | Fail |  | Fail |  | #12 | Once selected the resolution button with tab, the button cannot be opened with enter.
|  | Functional | Resolution - open dropdown list with space |  | Check whether the user can open the dropdown list with space | VG-T166 | Balázs |  |  |  | Pass |  | Pass
|  | Functional | Resolution - default value |  | Check whether the size of the game's window and the default value of the resolution button is the same | VG-T165 | Balázs |  |  |  | Pass |  | Pass
8 | Main menu Extra function | Functional | Main menu - open the menu from game |  | Check if main menu can be opened from game | VG-T186 | András |  |  |  | Pass |  | Pass
|  | Functional | Background music volume slide control with the scroller |  | Try to change the volume slide with the mouse scroller | VG-T180 | Gergő | Pass |  | Pass
|  | Functional | Background music volume slide control with arrows |  | Try to change the volume slide with the arrows | VG-T178 | Gergő | Pass |  | Pass
|  | Functional | Background music volume slide control with mouse |  | Try to change the volume slide with the mouse scroller | VG-T179 | Gergő | Pass |  | Pass
|  | Functional | Option menu - Full screen |  | The application is displayed in full screen or not | VG-T164 | Dina |  | Fail |  |  | Fail |  |  | #5 | The full screen option at the main menu is not actually full screen.
|  | Functional | Mute buttons with keys. |  | Test whether the mute button can be activated. | VG-T162 | Dina |  | Pass |  |  | Pass
|  | Functional | Mute buttons with mouse. |  | Test whether the mute button can be activated. | VG-T163 | Dina |  | Pass |  |  | Pass
|  | Functional | Operation of menu buttons with keys (Arrows) |  | Test whether these buttons are selectable | VG-T158 | Dina |  | Blocked |  |  | Blocked
|  | Functional | Operation of menu buttons with keys (TAB) |  | Test whether these buttons are selectable | VG-T157 | Dina |  | Blocked |  |  | Blocked
|  | Functional | Operation of menu buttons with the mouse |  | Test whether these buttons are selectable | VG-T156 | Dina |  | Blocked |  |  | Blocked

## Status
Req. ID | (Multiple Items)
Count of Req. Status | Requirement Type
Req. Status