## Munkalap1
Project overview
Project basic information
Project Name |  | Dungeon Crawl Team 3
Product Name |  | Dungeon Crawl Team 3
Product Description |  | Roguelikes are one of the oldest types of video games, the earliest ones were made in the 70s, they were inspired a lot by tabletop RPGs. The task will be to create a roguelike!
Project Description |  | Mission of the project
Test and verify the product.
The output product of the project
Test summary report and evaluation
Conduced by
Ecsedi Sándor ( Manual tester 33 )
Tischler Edina ( Manual tester 9 )
Veres Gergő ( Manual tester 11 )
Kiss Balázs ( Manual tester 77 )
Dudás Bence ( Manual tester 8)
Terecskei András ( Manual tester 12 )
Project Duration |  | Start date | 2021-01-25 | End date | 2021-02-05
Test cycles | Date of test cycle | Total number of test cases | Total number of executed test cases | Total number of passed test cases | Total number of failed test cases
Cycle #1 | 2021-01-27 | 36 | 36 | 36 | 0
Cycle #2 | 2021-01-28 | 43 | 43 | 39 | 4
Cycle #3 | 2021-02-01 | 69 | 69 | 51 | 14
Cycle #4 | 2021-02-03 | 77 | 77 | 50 | 11